## testplan
Testplan

## TestCase
Product Name |  | skincarisma.com | TC Start Date | 2024-01-04 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 17/04/2024 | TC Execution End Date | - - |  |  |  |  | PASS | 35
Epic |  |  | Test Case Developed By | Fahema Akter | Browser (tested) | Yes |  |  |  |  | FAIL | 6
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | NO |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 41
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'skincarisma,com' 3. Go to the website. |  |  | Passed
2 |  | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation. | None | 1. Goto the URL https://www.semrush.com/website/skincarisma.com/overview/?source=trending-websites 2. Click on the Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | It should be as per the requirement | Found as per expectation. | None | 1. Goto the URL https://www.semrush.com/website/skincarisma.com/overview/?source=trending-websites 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation. | None | 1. Goto the URL https://www.semrush.com/website/skincarisma.com/overview/?source=trending-websites 2. Check red asterisk beside mandatory field |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation. | None | 1. Goto the URL https://www.semrush.com/website/skincarisma.com/overview/?source=trending-websites 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation. | None |  |  |  | Passed
7 |  |  |  | Checkbox beside 'Receive Semrush news and SEO tips' | Checkbox should be present | Found as per expectation. | None |  |  |  | Passed
8 |  |  |  | checking Checkbox and Remember Me are present | Checkbox And Remember me should be present | Not Found as per expectation. | None | 1. Goto the URL https://www.semrush.com/website/skincarisma.com/overview/?source=trending-websites 2. click the signup button in the top right corner 3. Check the 'Remember Me' and checkbox not found | https://prnt.sc/-RAukjC2opLe |  | Failed
9 |  |  |  | Checking 'Receive Semrush news and SEO tips' checkbox is not enabled by default | Should not be enabled by default | Found as per expectation. | None | N/A |  |  | Passed
10 |  | Functional testing | Sign up | Keeping mandatory fields blank | Should be as per the requirement | Found as per expectation. | None | N/A |  |  | Passed
11 |  |  |  | Checking the Email and password fields is case-insensitive | Should not accept the provided input | Found as per expectation. | email:AAanjbjhAJHH password:hsvdhaAJJBSLK_NDNFKJD |  |  |  | Passed
12 |  |  |  | Entering blank at first position in Email and password field | Should not accept the provided input | Found as per expectation. | Email: forthbase12@yopmail.com password: FAHIMA_GMAIL.com | 1. Goto the URL https://www.semrush.com/signup/?src=header 2. Click on sign up button at the right corner 3. Input space at first position of Email and Password | https://prnt.sc/WpBDTw4U5fCH |  | Failed
13 |  |  |  | Verify all fields related to registration present on the SIGN UP form. | Should be as per the requirement | Found as per expectation. | None |  |  |  | Passed
14 |  |  |  | Password field should have validation for a minimum of 8 to maximum of 16 characters, must contain one special character, at least one uppercase character, and have a numerical. | Should be as per the requirement | Found as per expectation. | Email:forthbase12@yopmail.com passsword:AABB_GMAIL.COM |  |  |  | Passed
15 |  |  |  | Verify password added by the user should be protected, encrypted, and shown in an asterisk(***). | Should be as per the requirement | Found as per expectation. | None |  |  |  | Passed
16 |  |  |  | Verify whether the validation is added for the password and confirm whether passwords are the same or not | Should not Found as per requirement | Found as per expectation. | None | 1. Goto the URL https://www.semrush.com/signup/?src=header 2. Click on sign up button at the right corner 3.confirm passwoed is missing | https://prnt.sc/UtwQuRCmOen2 |  | Failed
17 |  |  |  | Verify an eye icon added to the password and confirm the password field. | Should be as per the requirement | Found as per expectation. | None |  |  |  | Passed
18 |  |  |  | Verify by clicking on the eye icon password should be shown for both passwords and confirm password fields. | Should be as per the requirement | Found as per expectation. | None |  |  |  | Passed
19 |  |  |  | verify sign up with right email and password | Should be as per the requirement | Found as per expectation. | Email: forthbase12@yopmail.com password: FAHIMA_GMAIL.com |  |  |  | Passed
20 |  |  |  | verifying sign up using 1 character in the email field | Should not accept the provided input | Not Found as per expectation. | Email: f@yopmail.com password: FAHIMA_GMAIL.com | 1. Goto the URL https://www.semrush.com/signup/?src=header 2. Click on sign up button at the right corner 3.fill 1 character in the email field | https://prnt.sc/svV0pVTyQTPG |  | Failed
21 |  |  |  | Validating an email id can only be used one time | Should be as per the requirement | Found as per expectation. | None |  |  |  | Passed
22 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Not Found as per expectation. | email:fahima@gmail.com password:ajdfkdhkjdbjJHH_KJFG | 1. Goto the URL https://www.semrush.com/signup/?src=header 2. Click on sign up button at the right corner 3.fill Email field with invalid mail | https://prnt.sc/FeXPTNBR84Mp |  | Failed
23 |  |  |  | Validating an email id can only be used one time | Should not accept the provided input and display an error message | Found as per expectation. | Email: forthbase12@yopmail.com password: FAHIMA_GMAIL.com |  |  |  | Passed
24 |  |  |  | Inputing weak password length | Should allow user to register | Found as per expectation. | hhg#k88 |  |  |  | Passed
25 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation. | john8888_24 |  |  |  | Passed
26 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation. | hgjkgjkjkjh!&*77 |  |  |  | Passed
27 |  |  |  | Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation. | "Password: john@8888 Confirm password: jnn8888" |  |  |  | Passed
28 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | jamee999 |  |  |  | Passed
29 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field |  |  |  | Passed
30 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field |  |  |  | Passed
31 |  | Functionality Testing | Sign In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found not as per expectation. | N/A |  |  |  | Passed
32 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation. | john@8888 |  |  |  | Passed
33 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation. | email:hgsdhsfv@gmail.com password:hgsdhsfv%32 |  |  |  | Passed
34 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found not as per expectation | email: monkeytype@yopmail.com password:monkeytype@yopmail.com |  | https://prnt.sc/_zn1m0nA56z9 |  | Failed
|  |  |  | Checking by selecting ‘Forgot Password’ multiple times | Should sent an email for recovering password | Found as per expectation | N/A |  |  |  | Passed
35 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A |  |  |  | Passed
36 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found not as per expectation | N/A |  |  |  | passed
37 |  |  |  | Enabling the 'Show Password' checkbox of 'Set a New Password' | Password should be dispayed | Found as per expectation | N/A |  |  |  | Passed
38 |  |  |  | Verifying inputing old password on 'Set a New Password' | Should not allow user to login and display an error message | Found as per expectation |  |  |  |  | Passed
39 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation |  |  |  |  | Passed
40 |  |  |  | Checking if the link gets dissolved setting a new password | Link should get dissolved | Found not as per expectation. |  |  |  |  | Passed
41 |  |  | Improvement Scope | A maximum length of the password should be defined if user put the max value
42 |  |  |  | In the login field the eye icon should be present for the user's convenience
43 |  |  |  | Social media links may be in include under the login section
44 |  |  |  | In signup page more information should be attach for security purpose.
45 |  |  |  | Add captcha on signup page
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Bug Report
BUG REPORT
# SL 01
Issue:checkbox missing in sign up page
Reproducing Steps:
1. Goto the URL https://www.semrush.com/website/skincarisma.com/overview/?source=trending-websites 2. Click on the Register button at the right corner 3. Check the spelling and grammar of the website
Env: Testing
Module: Sign Up
Severity: P3
screenshot: checkbox error
Responsible QA:Fahema akter
BUG REPORT
# SL 02
Issue:checkbox missing in sign up page
Issue:Entering blank at first position in Email and password field
Reproducing Steps:
1. Goto the URL https://www.semrush.com/signup/?src=header 2. Click on sign up button at the right corner 3. Input space at first position of Email and Password
Env: Testing
Module: Sign Up
Severity: P2
blankspace error
Responsible QA:Fahema akter
BUG REPORT
# SL 03
Issue:Confirm password missing in sign up page
Reproducing Steps:
1. Goto the URL https://www.semrush.com/signup/?src=header 2. Click on sign up button at the right corner 3.confirm passwoed is missing
Env: Testing
Module: Sign Up
Severity: P2
screenshot:cronfirmpassword error
Responsible QA:Fahema akter
BUG REPORT
# SL 04
Issue:Take 1 character in email field in sign up page
Reproducing Steps:
1. Goto the URL https://www.semrush.com/signup/?src=header 2. Click on sign up button at the right corner 3.fill 1 character in the email field
Env: Testing
Module: Sign Up
Severity: P2
screenshot:1 character error
Responsible QA:Fahema akter

## test metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (41/41)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/41)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (35/41)*100 = 85.39
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (6/41)*100 = 14.60
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/62)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A